## Risk-Issues
High Risk
Med Risk | Project - Issues and Risks | [7 empty] | DashBoard?
Low Risk | Item # | Issue/Risk | Description | Resolution Plan / Mitigation Plan | Contingency Plan | Due Date | Risk Owner | MPP Task
| R-1 | Risk - RR | Copy Database failure if it does then the testing gets pushed back a week . | 1) Provide functionality to have redunandcy for copying the database in case of a failure due to resons of caching, memory or due to piping and web service failing while during copying database. | 1) Have Database copying during non-hours of operation until database is copied correctly and no failure happens with functionality provided to allow for this | 2021-06-02 | OIT Director | Task 170 | N
| R-2 | Risk - MW | It may take longer than 14 days to set up all communications and approval with religious shelters as each shelter may have limited resources available to maintain expediant communication. This could set the Core Functionalities Requirements Document back. | 1) Automate follow-up e-mails to get responses if a response is not received after 3 days 2) Reach out to partnering religious shelters and community centers to see if there is a way to set up communication via partners 3) Maintain up-to-date communication with Relations Manager | Continue to set up communications and approvals from shelters as soon as they become available. Commonalities among shelters may arise and can be soft-included into relevant requirements until they are approved. Keep Relations Manager on payroll for communications acquistion for as long as necessary. | 2020-12-11 | Relations Manager | Task 40 | N
| R-3 | Risk - RA | Evacuation routes provided by cities don't include rural areas or are inaccurate. This can causes problems during the turn by turn developement and push back the end date. | Include mutliple driving route from governement agencies and busnisses such as the post office and amazon | Contact local authorities in the unincluded or inaccurate areas and get evacuation routes from them | 2021-02-01 | Project Manager | Task 120 | N
| R-4 | Risk - AD | User receives two copies of turn by turn directions when testing load sharing during the Load sharing tests | Setup policy to only allow user to sign into a single server at a time to force the user to signout of a server before allowing sign on to another | When load sharing is initiated, instead of moving data, simply close the session on one server before starts a new session on another | 2021-08-13 | OIT Director | Task 181 | N
| R-5 | RISK - RR | Test Different Screen Sizes because some screen sizes might create UI failures depedning on non-proportional screens that exists. If non-proportioned sized screens exist as a users screen then there needs to be remdiation for this due to UI failing due to non-proportioned size screens viewing content through the APP. | 1) Allow for functionality of testing for all screen size. 2) Have functionality made for all screen resolutions and for all types of modality of screen types. | 1) Use Automated testing tools for screen sizes and compaitibility issues based onscreen sizes for testing purposes. 2) Manual tesing of the most common screen sizes and then testing abnormal resolution screen sizes in a virtual Environment rather than physical. | 2021-10-06 | OIT Director | Task 184 | N
| R-6 | Risk - NP | During API Testing, we find that the open-source APIs have been changed and need to be redesigned. This can delay deployment significantly. | Keep a list of all the sources that we are using to get data from and ensure that any upcoming changes are reviewed by the design and development lead. | The Design Lead will update the API design and forward the Change Requests to the Development team to implement the new API data | 2021-08-09 | Design Lead | Task 171 | N
| R-7 | Risk - NP | During Testing, the database is overloaded and fails, causing the testing team to not be able to test for 2-3 days, pushing back the API testing. | 1) Have the lead testing engineer review the resources on a weekly basis to make sure that we are not approching the limits 2) Create a backup of all the data and code in the testing environment on a different server weekly during the project scope and monthly during maintenance. | 1) Report the event to the Project Manager 2) Find out what caused the testing environment to fail 3) Restore the environment back to the latest stable check point 4) Find out what steps need to be taken to prevent future failures | 2021-07-29 | Testing Lead | Task 177 | N
| R-8 | Risk - NP | During development, the database maximizes on storage, limiting the dev team from being able to setup dummy data and make any progress with development. | 1) Have the development lead and project manager review the resources on a weekly basis to make sure that we are not approching the limits or a point of failure 2) Create a backup of the code and projects on a daily basis on Github or an alternate to ensure stability of the data on the cloud | 1) Report the event to the Project Manager 2) Find out what caused the development environment to fail 3) Restore the environment back to the latest stable check point 4) Find out what steps need to be taken to prevent future failures | 2021-02-22 | Development Lead | Task 119 | N
| R-9 | Risk - RA | Mailing delays cuase legal documents to be approved and finalize later than expected. This can push back start of the projects development. | 1) Have the documents personally dropped off by someone on the project or a stakeholder. 2) Track the mail to insure that it's moving on time. 3) Mail a second document using a different mail carrier to increase the odds of them arriving on time. | Find current location of the document, see how long the mailing delay is, and if there's anyway to expidite the mailing. If the delay is longer than it'd take to resend the documents, remail the documents using another provider or deliver them in person. | 2021-03-08 | Requirenments Lead | Task 50 | N
| R-10 | Risk - RA | Shelter recommendations from navigation may conflict with shelter information filter. This can cause issues during the escape route testing | 1) Prioritize perfered shelters over the nearest located shelter 2) Applied filtered shelters the navigator recommendations even if it hides nearby shelters. | Provide a default escape route away from the natural distaster if no shelters appear. This route will be determinded by the direction of the distaster and the locations of any user contacts. | 2022-08-02 | Deployment Lead | Task 155 | N
| R-11 | Risk - AD | It may take longer than 20 days to acquire employees and resources to start the project which may delay the start of the requirements phase | Prioritize hiring requirement engineers so that requirements can be started and the project can start. | Split the hiring group so that some can start on burst requirement activities so that when new members are hired they can immedietly begin working | 2020-11-23 | Project Manager | Task 8 | N
| R-12 | Risk - MW | Manual data input for copying the database for development (Task 110) will likely take longer than 5 days with one person on the job. This could delay backend development database setup (Task 125), which could snowball into delaying backend testing (Tasks 170, 177). | Keep updated file of data that will need to be manually input | Use available 4 days from slack with OIT Director to complete database setup and copying | 2021-05-24 | OIT Director | Task 110 | N
| R-13 | Risk - AD | During design of the Users schema, the superkey reveals too much user information which breaks legal requirements. This could cause a delay in the time taken to design the User schema | Include profile pictures for identification and unique user ids that can be shared to ensure connections are being made to the right user and location data is not being shared to unwanted people | Authenticate users through contacts and phone numbers to ensure correct member is being added which reduces superkey length | 2021-04-05 | Design Lead | Task 81 | N
| R-14 | Risk - MW | Client unsure of whether or not the project will use open source navigation software. Whether or not third-party software is used may affect requirements elicitation for Navigation Requirements Draft. This could delay completion of the Navigation Requirements Draft (Task 43), which can then delay completion of User-to-User Communications Requirements Draft (Task 44). 2 days will likely not be enough time for both making this decision and forming the requirements around it. ReqEng_1 - Lead will only be available for 2 days on Task 44 before moving to Task 33, unless we burn in to overtime. | 1) Research to anticipate what requirements may be necessary for different types of third-party navigation software 2) Find list of potential third-party softwares to use 3) Find consultant who may be able to expedite elicitation | 1) Use 4 days of slack (1/23/21 - 1/24/21, 1/27/21, 1/30/21) to elicit requirements 2) Bring in consultant to shed light on any concerns in order to expedite elicitation | 2021-01-22 | Project Manager | Task 43 | N
| R-15 | Risk - RR | TESTER_3 is new and a recent graduate out of university. That said we will Have TESTER_3 to collaborate with TESTER_1- LEAD to validate TESTER_3s work as he is not as experienced as others such as Tester_1- LEAD , Tester_2 and Tester_4. The risk is Tester_3's ability to perform and complete assigned tasks. | 1) Provide and reinforce security principles for Security Testing and also have TESTER_3 be given TRAINING on the weekends by the TESTER_1 -LEAD in the area specifically relating to Security for Mobile Applications to better his capabilities to fully acheive his tasks to completion in a timely manner. 2) Hire outside Security Trainer and world renound Tester to guide TESTER_3 to enhance his abilities to better performe at his job for security and Testing. | 1) Have Tester_3 and Tester_1 - Lead work together to complete tasks and also to help grow Tester_3's abilities to perform without extra help in the Testing realm of security. | 2021-07-15 | OIT Director | Task 179 | N
| R-16 | Risk - MW | Architect 1 not up to date with current risk analysis best practices. This could slow down conducting architecture risk analysis (may take longer than 2 days) | 1) Have Architect research architecture risk analysis in the weeks prior to security design 2) Find list of potential security consultants to bring in | 1) Bring in security consultant | 2021-05-25 | Project Manager | Task 103 | N
| R-17 | Risk - MW | 3 days for penetration testing must also include vulnerability testing (vulnerability testing to happen directly before pen-testing). Original timeline may not be enough time to complete both of these tasks, which could push back end-to-end testing | 1) Get definitive answer from Testing lead on how much time will be necessary for pen-testing and vulnerability testing 2) Keep Tester lead on stand-by for potentially doing vulnerability testing after completing security test cases 3) Split up penetration testing and vulnerability testing into seperate tasks each with their own dedicated times. | 1) Having Tester_1 - Lead complete vulnerability testing after security test cases are completed | 2021-10-11 | Testing Lead | Task 190 | Y
| R-18 | Risk - RR | Disaster preperation reccomendations page (Task 156) might need more time to finish due to pulling data from the web would require possibly more time to complete as filtering data from web requires more functionality to keep on schedule. This could require more than 5 days. The risk is failure to meet deadline on due date. | 1) Ask other resources to contribute one day such as the Dev_1 and Dev_2 as they have some time after completing Tasks 146 and Tasks 147. 2) Require Dev_4 and Dev_5 the primary resources working on the Disaster Preperation recommendation Page Task to work on the weekend of SATURDAY 8/28/2021 and SUNDAY 8/29/2021 for 8 hours each day on the weekend. 3) Hire outside consultant to berate Developers and train them how to program their code and optimize their code through EXTREME PROGRAMMING practices to finish 7 days of work in 5 days. | 1) Have EMERGENCY MEETING ON the weekend to make DEV_1, DEV_2, DEV_3, DEV_4 and DEV_5 complete the TASK 151 on one day specifically on 8/29/2021 to make the minimum amount of programming required to provide the CORE functionality for the DISASTER PREPERATIONS PAGE TASK 151. | 2021-10-05 | Development LEAD | Task 156 | Y
| R-19 | Risk - RA | The way delete Resorce setup is designed may cause problems when testing the user information display due to user being able link to their family accounts and shelters. This could extend user information display testing. | 1) Have the data base use phantom deletion. 2) If data field is empty after resorce deletion, remove data field from user page. | Have a back up of the previous resorce to use in place of the deleted one and send a deletionn message to the page owner. | 2021-04-23 | Design Lead | Task 69 | N
| R-20 | Risk - RA | Equipment checklist page for core functionalities developement occurs before the checklist is connected from backend. Depending on the backend clecklist requirenments, development may have to go back and make additional changes. | With developer 4 working on both tasks, have developer 4 be the main lead on the core functionality checklist | Have developer 4 revise the functinality checklist after the Friday backend requiernments are done, 8/5/21 | 2021-07-19 | Design Lead | Task 101 | N
| R-21 | Risk - RR | Publish To App Store might take longer than the time aloted for TASK 202. Publishing To an APP store requires verification and other parts as an APP Store tries to keep quality among Apps and to validate legitamte APPs on their market Place. We MIGHT, COULD, POSSIBLY need to move the the PUBLISHING of the APP by at least 7 days to meet the mark. DEPLOYEMENT_LEAD_1 will be required to work. | 1) Ask Deployement Lead to work an extra day on a week and a half in advanced to meet the deadline for Publishing app. 2) Make DEPLOYEMENT_LEAD_1 work 4 weekends in a row to accomodate 7 days of review for APP from GOOGLE play store. starting on 9/20/2021 up until 11/10/2021. | 1) Force Deployement_Lead_1 to work on the Weekends starting on 9/20/2021 up until 11/10/2021. | 2021-11-10 | Deployement Lead | Task 202 | Y
| R-22 | Risk - MW | No Architects have been scheduled for Pages and Wireframes during Design Document Draft for Front End. Lack of Architect availability could lead to incorrect documentation by developers, redocumentation by Architects, and delay Design Document Draft for Front End. | 1) Arch_3 becomes available 4/20/21 - 6/16/21. See if they are able and willing to take on extra hours in order to help developers in creating Pages and Wireframes. 2) If Arch_3 is unavailable, speak with Arch_1 and Arch_2 to work a few extra weekends. 3) Set up a way for developers to rate their comfort level (1 - 5) with the pages and wireframes, and have them send rating to Project Manager at the end of each work day. If a rating falls below 5, bring in an architect the soonest day possible and have developers send the pages and wireframe questions to lead architect and CC Project Manager. | Have Arch_1, Arch_2, Arch_3 work any days available. | 2021-05-04 | Design lead | Task 84 | N
| R-23 | Risk - MW | Testers are unsure about security testing - may take longer than 9 days to fully complete Security Testing (such as the security test cases, dynamic analysis, and penetration testing) without up-to-date knowledge on current best practices. | 1) Coordinate with lead tester to find and distribute security modules for Tester_1, Tester_2, and Tester_3 to complete at home. 2) If no modules are formed within 2 days of of working with Tester_1 - Lead, bring in security consultant to expedite the process. 3) Have security consultants listed in case we need to outsource security testing. | Outsource security testing, have them start between 10/5/2021 and 10/12/2021 depending on how far testers get in security testing. | 2021-10-05 | Testing Lead | Task 187 | Y
| R-24 | Risk - AD | While aquiring data for shelters, some shelters cannot provide all information required to fulfill superkey for their object. This might require a redesign of the schema for that object. The schema has already been designed once and we would now have to spend time designing it again which would take away time from the developers current task. | Integrate design of Schemas with acquisition of data to better understand available data. This will allow more mindful design of schemas | List missing columns as Unknown which will have to be reflected on the front-end. Or the Front-end will have to be amended to only include non-null parameters | 2021-02-22 | Requirements Lead | Task 76/119 | N
| R-25 | Risk - AD | If shelter data has anomolies then the front-end development may take longer to handle null values and alter the display to prevent null-values from being displayed to the user. This is because instead of showing blank fields, we would want to hide them all together. This is additional work for the developers to do that was not accounted for in the initial schedule. The front-end development tasks may take longer than expected and this would push the critical path. | Include fake bad data within the database whether or not bad data will occur to ensure front-end has capabilities to handle it. This forces the developers to factor in the cost of this development within the schedule which will allow them to better plan their time. | Always display missing parameters in the front-end as unknown instead of hiding the field. This will reduce overall quality but will save time and money | 2021-06-25 | Development Lead | Task 145 | N
| R-26 | Risk - NP | During end to end, we might have non-functional requirements that can't be tested by the testers because of lack of experience or knowledge. This could delay deployment significantly. | Plan ahead for what libraries and language will be used for testing and ensure that the testers have ample time to get acquainted with the testing technology before the devs finish their work. | If testers are not knowledgeable on the technology, we could ask the stakeholders if there are any testers who have worked with this technology before to help the current testing team. | 2021-10-12 | Testing Lead | Task 191 | N
| R-27 | Risk - NP | During the quality report, it's found that the developers failed to meet the non-functional requirements. This would delay development and testing, thus pushing the critical path. | Upon design completion, inform the developers of any non-functional requirements that they must meet and keep that as a check during the weekly meetings. | If the non-functional requirements are not met, the PM, development lead, developer, and design lead should get on a call and find the.most efficient method to meet the requirements and ensure a successful implementation. | 2021-10-28 | Development Lead | Task 202 | N
| R-28 | Risk - NP | If FEMA announces that we can no longer use one of our previous data services from a specific company (like IBMWeather) then it could delay API testing by at least 7 days. | On a monthly basis, ensure that FEMA is updated on all the services, company, vendors, and resources the project is using and that they are satisfied with any changes or usage. | If a sudden change in US government policies prohibits use of a specific tool or service, we must submit a change request and ask FEMA for more resources, time, and money for implementing the change. | 2021-05-06 | Project Manager | Task 159, 179 | Y
| R-29 | Risk - RA | Due to there being no security documentation during the testing phase its self, more time is needed to reverse engineer and create the security documents. This will increase the time spent on creating the finalized security document | Have the security testing team create a security document that describes how the security was actually implemented. | Create a meeting with the final security documentation team and the security testing team to go over the current state of secuirty. | 2021-10-25 | Deployment Lead | Task 200 | Y
| R-30 | Risk - MW | The approved security consultant for the Security Design Document may be unable to show up until 6/24/21, which is well after the due date for the completion of the Design Document. This could delay the Securty Design Document by 23 days. | 1) E-mail approved security consultant to gain priority scheduling for May, 2021. 2) Get at least three more security consultants approved by FEMA and put on a tenative schedule for May. 3) Consider permanently changing security consultants for the Security Design Document - discuss with FEMA. | Completely change security consultants. | 2021-03-15 | Project Manager | Task 103 | Y
| R-31 | Risk - AD | There is little to no slack time between completing the front end pages and connecting those pages with backend resources. This might cause delays to propogate and delay the critical path of the project | Add resources to front end page development to reduce time to completion to allow for slack | Add resources on following tasks that are affected to bring them back to speed | 2021-08-10 | Project Manager | Task 133 | Y
| R-32 | Risk - RR | The Ensure rejection of DB access by anywhere else Task 195 might need more time to complete the deployement of the rejection of Database access due to the amount of validation and verification that is needed to be deployed with the Ensure rejection of DB access by anywhere else Task 195. This task might, coukd, possibly take more time than 10 days. The risk is failure to meet deadline on the due date. | 1) Ask Deployement Lead to work on the Task 195 on weekends to accomodate the time that might,could,possibly be needed to complete the task 195 on time. 2) Give speciliazed training on HOW TO DEPLOY FASTER and MORE FFICIENT from Deployement Lead to Deployment_Engineer_2 so that the deployement for the task 195 can meet the deadline of 10 days rather than past 10 days of work. | Add resources from other Tasks that complete their Tasks early that are in the deployement team to make task 195 to be completed on schedule. | 2021-11-03 | Deployement_Lead | Task 195 | Y
Project - Issues and Risks -- CLOSED
| Item # | Issue/Risk | Description | Resolution Plan / Mitigation Plan | Close Reason | Date Closed | Closed By
| R-1 | Risk - RR | Copy Database failure if it does then the testing gets pushed back a week . | 1) Provide functionality to have redunandcy for copying the database in case of a failure due to resons of caching, memory or due to piping and web service failing while during copying database. | 1) Have Database copying during non-hours of operation until database is copied correctly and no failure happens with functionality provided to allow for this | 2021-06-02 | OIT Director | Task 170 | N
| R-2 | Risk - MW | It may take longer than 14 days to set up all communications and approval with religious shelters as each shelter may have limited resources available to maintain expediant communication. This could set the Core Functionalities Requirements Document back. | 1) Automate follow-up e-mails to get responses if a response is not received after 3 days 2) Reach out to partnering religious shelters and community centers to see if there is a way to set up communication via partners 3) Maintain up-to-date communication with Relations Manager | Continue to set up communications and approvals from shelters as soon as they become available. Commonalities among shelters may arise and can be soft-included into relevant requirements until they are approved. Keep Relations Manager on payroll for communications acquistion for as long as necessary. | 2020-12-11 | Relations Manager | Task 40 | N
| R-3 | Risk - RA | Evacuation routes provided by cities don't include rural areas or are inaccurate. This can causes problems during the turn by turn developement and push back the end date. | Include mutliple driving route from governement agencies and busnisses such as the post office and amazon | Contact local authorities in the unincluded or inaccurate areas and get evacuation routes from them | 2021-02-01 | Project Manager | Task 120 | N
| R-7 | Risk - NP | During Testing, the database is overloaded and fails, causing the testing team to not be able to test for 2-3 days, pushing back the API testing. | 1) Have the lead testing engineer review the resources on a weekly basis to make sure that we are not approching the limits 2) Create a backup of all the data and code in the testing environment on a different server weekly during the project scope and monthly during maintenance. | 1) Report the event to the Project Manager 2) Find out what caused the testing environment to fail 3) Restore the environment back to the latest stable check point 4) Find out what steps need to be taken to prevent future failures | 2021-07-29 | Testing Lead | Task 177 | N
| R-8 | Risk - NP | During development, the database maximizes on storage, limiting the dev team from being able to setup dummy data and make any progress with development. | 1) Have the development lead and project manager review the resources on a weekly basis to make sure that we are not approching the limits or a point of failure 2) Create a backup of the code and projects on a daily basis on Github or an alternate to ensure stability of the data on the cloud | 1) Report the event to the Project Manager 2) Find out what caused the development environment to fail 3) Restore the environment back to the latest stable check point 4) Find out what steps need to be taken to prevent future failures | 2021-02-22 | Development Lead | Task 119 | N
| R-9 | Risk - RA | Mailing delays cuase legal documents to be approved and finalize later than expected. This can push back start of the projects development. | 1) Have the documents personally dropped off by someone on the project or a stakeholder. 2) Track the mail to insure that it's moving on time. 3) Mail a second document using a different mail carrier to increase the odds of them arriving on time. | Find current location of the document, see how long the mailing delay is, and if there's anyway to expidite the mailing. If the delay is longer than it'd take to resend the documents, remail the documents using another provider or deliver them in person. | 2021-03-08 | Requirenments Lead | Task 50 | N
| R-11 | Risk - AD | It may take longer than 20 days to acquire employees and resources to start the project which may delay the start of the requirements phase | Prioritize hiring requirement engineers so that requirements can be started and the project can start. | We were able to successfully hire all resources within the deadline | 2020-11-23 | Project Manager
| R-12 | Risk - MW | Manual data input for copying the database for development (Task 110) will likely take longer than 5 days with one person on the job. This could delay backend development database setup (Task 125), which could snowball into delaying backend testing (Tasks 170, 177). | Keep updated file of data that will need to be manually input | Use available 4 days from slack with OIT Director to complete database setup and copying | 2021-05-24 | OIT Director | Task 110 | N
| R-13 | Risk - AD | During design of the Users schema, the superkey reveals too much user information which breaks legal requirements. This could cause a delay in the time taken to design the User schema | Include profile pictures for identification and unique user ids that can be shared to ensure connections are being made to the right user and location data is not being shared to unwanted people | Authenticate users through contacts and phone numbers to ensure correct member is being added which reduces superkey length | 2021-04-05 | Design Lead | Task 81 | N
| R-14 | Risk - MW | Client unsure of whether or not the project will use open source navigation software. Whether or not third-party software is used may affect requirements elicitation for Navigation Requirements Draft. This could delay completion of the Navigation Requirements Draft (Task 43), which can then delay completion of User-to-User Communications Requirements Draft (Task 44). 2 days will likely not be enough time for both making this decision and forming the requirements around it. ReqEng_1 - Lead will only be available for 2 days on Task 44 before moving to Task 33, unless we burn in to overtime. | 1) Research to anticipate what requirements may be necessary for different types of third-party navigation software 2) Find list of potential third-party softwares to use 3) Find consultant who may be able to expedite elicitation | 1) Use 4 days of slack (1/23/21 - 1/24/21, 1/27/21, 1/30/21) to elicit requirements 2) Bring in consultant to shed light on any concerns in order to expedite elicitation | 2021-01-22 | Project Manager | Task 43 | N
| R-15 | Risk - RR | TESTER_3 is new and a recent graduate out of university. That said we will Have TESTER_3 to collaborate with TESTER_1- LEAD to validate TESTER_3s work as he is not as experienced as others such as Tester_1- LEAD , Tester_2 and Tester_4. The risk is Tester_3's ability to perform and complete assigned tasks. | 1) Provide and reinforce security principles for Security Testing and also have TESTER_3 be given TRAINING on the weekends by the TESTER_1 -LEAD in the area specifically relating to Security for Mobile Applications to better his capabilities to fully acheive his tasks to completion in a timely manner. 2) Hire outside Security Trainer and world renound Tester to guide TESTER_3 to enhance his abilities to better performe at his job for security and Testing. | 1) Have Tester_3 and Tester_1 - Lead work together to complete tasks and also to help grow Tester_3's abilities to perform without extra help in the Testing realm of security. | 2021-07-15 | OIT Director | Task 179 | N
| R-16 | Risk - MW | Architect 1 not up to date with current risk analysis best practices. This could slow down conducting architecture risk analysis (may take longer than 2 days) | 1) Have Architect research architecture risk analysis in the weeks prior to security design 2) Find list of potential security consultants to bring in | 1) Bring in security consultant | 2021-05-25 | Project Manager | Task 103 | N
| R-19 | Risk - RA | The way delete Resorce setup is designed may cause problems when testing the user information display due to user being able link to their family accounts and shelters. This could extend user information display testing. | 1) Have the data base use phantom deletion. 2) If data field is empty after resorce deletion, remove data field from user page. | Have a back up of the previous resorce to use in place of the deleted one and send a deletionn message to the page owner. | 2021-04-23 | Design Lead | Task 69 | N
| R-20 | Risk - RA | Equipment checklist page for core functionalities developement occurs before the checklist is connected from backend. Depending on the backend clecklist requirenments, development may have to go back and make additional changes. | With developer 4 working on both tasks, have developer 4 be the main lead on the core functionality checklist | Have developer 4 revise the functinality checklist after the Friday backend requiernments are done, 8/5/21 | 2021-07-19 | Design Lead | Task 101 | N
| R-22 | Risk - MW | No Architects have been scheduled for Pages and Wireframes during Design Document Draft for Front End. Lack of Architect availability could lead to incorrect documentation by developers, redocumentation by Architects, and delay Design Document Draft for Front End. | 1) Arch_3 becomes available 4/20/21 - 6/16/21. See if they are able and willing to take on extra hours in order to help developers in creating Pages and Wireframes. 2) If Arch_3 is unavailable, speak with Arch_1 and Arch_2 to work a few extra weekends. 3) Set up a way for developers to rate their comfort level (1 - 5) with the pages and wireframes, and have them send rating to Project Manager at the end of each work day. If a rating falls below 5, bring in an architect the soonest day possible and have developers send the pages and wireframe questions to lead architect and CC Project Manager. | Have Arch_1, Arch_2, Arch_3 work any days available. | 2021-05-04 | Design lead | Task 84 | N
| R-24 | Risk - AD | While aquiring data for shelters, some shelters cannot provide all information required to fulfill superkey for their object. This might require a redesign of the schema for that object. The schema has already been designed once and we would now have to spend time designing it again which would take away time from the developers current task. | Integrate design of Schemas with acquisition of data to better understand available data. This will allow more mindful design of schemas | List missing columns as Unknown which will have to be reflected on the front-end. Or the Front-end will have to be amended to only include non-null parameters | 2021-02-22 | Requirements Lead | Task 76/119 | N
| R-25 | Risk - AD | If shelter data has anomolies then the front-end development may take longer to handle null values and alter the display to prevent null-values from being displayed to the user. This is because instead of showing blank fields, we would want to hide them all together. This is additional work for the developers to do that was not accounted for in the initial schedule. The front-end development tasks may take longer than expected and this would push the critical path. | Include fake bad data within the database whether or not bad data will occur to ensure front-end has capabilities to handle it. This forces the developers to factor in the cost of this development within the schedule which will allow them to better plan their time. | Always display missing parameters in the front-end as unknown instead of hiding the field. This will reduce overall quality but will save time and money | 2021-06-25 | Development Lead | Task 145 | N
| R-28 | Risk - NP | If FEMA announces that we can no longer use one of our previous data services from a specific company (like IBMWeather) then it could delay API testing by at least 7 days. | On a monthly basis, ensure that FEMA is updated on all the services, company, vendors, and resources the project is using and that they are satisfied with any changes or usage. | If a sudden change in US government policies prohibits use of a specific tool or service, we must submit a change request and ask FEMA for more resources, time, and money for implementing the change. | 2021-05-06 | Project Manager | Task 159, 179 | Y
| R-30 | Risk - MW | The approved security consultant for the Security Design Document may be unable to show up until 6/24/21, which is well after the due date for the completion of the Design Document. This could delay the Securty Design Document by 23 days. | 1) E-mail approved security consultant to gain priority scheduling for May, 2021. 2) Get at least three more security consultants approved by FEMA and put on a tenative schedule for May. 3) Consider permanently changing security consultants for the Security Design Document - discuss with FEMA. | Completely change security consultants. | 2021-03-15 | Project Manager | Task 103 | Y

## Action Item
0
| Project Action List | [8 empty] | DashBoard?
| # | Description | Originator | Action Owner | Date Assigned | Date Needed | Date Closed | Comments | Status
| A1 | MW - Setup weekly recurring meetings for the Testing team | Project Manager | Madeline Wrzesinski | 2021-02-02 | 2021-03-01 | 2020-07-22 | To ensure that the testing team is working well together and software requirements are accurate and possible to meet | Done | N
| A2 | Setup meeting with customer and testing team to review RDD for UI/UX | Project Manager | Project Manager | 2021-04-02 | 2021-04-05 | 2020-07-22 | To ensure consistent feedback on UI/UX | Done | N
| A3 | NP - Setup weekly recurring meetings for the Development team | Project Manager | Nikhil Patil | 2021-02-01 | 2021-03-01 | 2020-07-09 | To ensure that the development team is working well together and there are least amoutn of roadblocks | Done | N
| A4 | NP - Create a quarterly report on the financial standing of the project | Project Manager | Nikhil Patil | 2021-01-01 | Every quarter | Project End | To provide stakeholders with information regarding the financial stability of the project and updated cost as the project progresses | In Progess | N
| A5 | AD - Build milestone completion reports with resources used vs expected | Project Manager | Arib Dhuka | 2021-03-25 | Every Milestone | Project End | Ensure that our estimated budget is correct and we are on track for spending and timeline | In Progess | N
| A6 | AD - Setup quality report meetings before deployment to ensure product meets expectations | Project Manager | Arib Dhuka | 2020-09-01 | 2021-12-01 |  | Ensure that our project meets guidlines and any last minute bugs and improvemnts can be provided | Not Started | N
| A7 | RA - Setup meetings when needed to address current project risks | Project Manager | Renee Al-Tabatabaie | 2021-01-01 | 2021-12-01 |  | To inform the apropriate parties of the current risk and create a plan to resolve them | In Progess | N
| A8 | RA - Create testing report bi-monthly | Project Manager | Renee Al-Tabatabaie | 2021-01-15 | Bi-monthly | 2021-12-05 | To ensure that testing is going smoothly | In Progess | N
| A9 | RR- Database needs to be re-indexed every prior to the half way point of the project due to growth of data used and from changes from the Development Team | Project Manager | Rafael Raymos | 2020-10-01 | 2020-12-09 | 2021-01-05 | To ensure and to validate work of database is in full proper working order for customers | Done | N
| A10 | RR - Development meeting to determine any problems and issues to resolve or fix. | Project Manager | Rafael Raymos | 2021-01-01 | Weekly | 2021-01-05 | To Provide monthly check on work and if any problems arise there is a meet to resolve or brainstorm on how to best deal with the problems of development. | Done | N
| A11 | MW - Setup Quality Attribute Workship with FEMA representatives and application stakeholders | Project Manager | Madeline Wrzesinski | 2021-06-01 | 2021-01-26 | 2021-01-28 | To capture quality attributes and core requirements for system architecture | Done | N
| A12 | RR- Setup meeting with a security consultation team to better understand possible security risks. | OIT Director | Rafael Raymos | 2020-11-01 | 2021-01-26 | 2021-01-22 | To gain a better understanding of security issues that we need to address during design and development | Done | N
| A13 | NP - Remove Connect page design if the project is getting delayed, as it's the lowest priority requirement for FEMA. | Project Manager | Nikhil Patil | 2021-04-23 | 2021-06-21 | 2021-06-23 | Allows us to make sure that we deliver the solution on time by restricting the scope as suggested by the stakeholders. | Done | N
| A14 | MW - Set up Security Module meeting with Tester_1 - Lead in order to form security learning modules for Tester_2 and Tester_3. | Project Manager | Madeline Wrzesinski | 2021-06-30 | 2021-08-30 |  | To ensure that testers have the learning materials needed in order to perform security testing. | Not Started | N
| A15 | AD - Add an extra developer to the requirements document drafts for the UI/UX to bring these tasks back to schedule | Project Manager | Arib Dhuka | 2020-12-10 | 2020-12-15 | 2020-12-14 | This was necessary because at our last project status updated we realized we were behind schedule on these tasks | Done | N
| A16 | RA - Set up meeting with developers 4 and 5, archetect 3, and tester 4 to create a higharchy when applying the shelter filter to the nativation system. | Project Manager | Renee Al-Tabatabaie | 2021-09-20 | 2021-09-27 |  | To ensure that navagtion protocols when fiding nearby shelters allign with the user's shelter filter | Not Started | N
| A17 | RR- Setup a meeting to discuss transition between Testing team and Deployement Team to have a final Quality report made before releasing the APP into production. | Project Manager | Rafael Raymos | 2021-08-31 | 2021-09-03 |  | To inform deployement of any wonky components or problems that may occur once deployement starts or is in progress. | Not Started | N
| A18 | Host a meeting with a FEMA developer or tech lead to ensure that the resources agreed upon at the start have not been changed because of any policy changes. | Project Manager | Nikhil Patil | 2021-06-07 | 2021-06-11 | 2021-06-11 | Ensures that no changes in policy will affect the development or deployment of the project. | Done | Y
| A19 | Create list of at least three security consultants to get approved by FEMA representative for Security Design Documents. | Project Manager | Madeline Wrzesinski | 2021-03-01 | 2021-03-15 | 2021-03-16 | Safeguards development and delivery of Securty Design Document on time. | Done | Y
| A20 | Schedual tech demo with FEMA representative | Project Manager | Renee Al-Tabatabaie | 2021-07-30 | 2021-09-29 |  | Ensure that any changes on FEMA's behalf be brought up during the meeting. | Not Started | Y
| A21 | Host meeting with testing lead to decide whether or not having employees specialize within a certain branch of testing would aid efficency. | Project Manager | Arib Dhuka | 2021-05-05 | 2021-07-27 | 2021-07-02 | This would lead to another action of moving around resources and estimate changes to project schedule and budget | Not Started | Y
| A22 | Setup meeting with Deployement Team to provide a finalization checklist for deployment of all components and modules based off Tasks. | Project Manager | Rafael Raymos | 2021-11-06 | 2021-11-09 |  | This would lead to another action of moving around resources and estimate changes to project schedule and budget | Not Started | Y
CLOSED ACTION ITEMS
| A1 | MW - Setup weekly recurring meetings for the Testing team | Project Manager | Madeline Wrzesinski | 2021-02-02 | 2021-03-01 | 2020-07-22 | To ensure that the testing team is working well together and software requirements are accurate and possible to meet | Done
| A2 | Setup meeting with customer and testing team to review RDD for UI/UX | Project Manager | Project Manager | 2021-04-02 | 2021-04-05 | 2020-07-22 | To ensure consistent feedback on UI/UX | Done
| A3 | NP - Setup weekly recurring meetings for the Development team | Project Manager | Nikhil Patil | 2021-02-01 | 2021-03-01 | 2020-07-09 | To ensure that the development team is working well together and there are least amoutn of roadblocks | Done
| A9 | RR- Database needs to be re-indexed every prior to the half way point of the project due to growth of data used and from changes from the Development Team | Project Manager | Rafael Raymos | 2020-10-01 | 2020-12-09 | 2021-01-05 | To ensure and to validate work of database is in full proper working order for customers | Done
| A10 | RR - Development meeting to determine any problems and issues to resolve or fix. | Project Manager | Rafael Raymos | 2021-01-01 | Weekly | 2021-01-05 | To Provide monthly check on work and if any problems arise there is a meet to resolve or brainstorm on how to best deal with the problems of development. | Done
| A11 | MW - Setup Quality Attribute Workship with FEMA representatives and application stakeholders | Project Manager | Madeline Wrzesinski | 2021-06-01 | 2021-01-26 | 2021-01-28 | To capture quality attributes and core requirements for system architecture | Done
| A12 | RR- Setup meeting with a security consultation team to better understand possible security risks. | OIT Director | Rafael Raymos | 2020-11-01 | 2021-01-26 | 2021-01-22 | To gain a better understanding of security issues that we need to address during design and development | Done
| A13 | NP - Remove Connect page design if the project is getting delayed, as it's the lowest priority requirement for FEMA. | Project Manager | Nikhil Patil | 2021-04-23 | 2021-06-21 | 2021-06-23 | Allows us to make sure that we deliver the solution on time by restricting the scope as suggested by the stakeholders. | Done
| A15 | AD - Add an extra developer to the requirements document drafts for the UI/UX to bring these tasks back to schedule | Project Manager | Project Manager | 2020-12-10 | 2020-12-15 | 2020-12-14 | This was necessary because at our last project status updated we realized we were behind schedule on these tasks | Done
| A18 | Setup a monthly meeting with a FEMA developer or tech lead to ensure that the resources agreed upon at the start have not been changed because of any policy changes. | Project Manager | Nikhil Patil | 2021-06-07 | 2021-06-11 | 2021-06-11 | Ensures the delivery of the project on time without disturbing the following activities in any significant way. | Done
| A19 | Create list of at least three security consultants to get approved by FEMA representative for Security Design Documents. | Project Manager | Madeline Wrzesinski | 2021-03-01 | 2021-03-15 | 2021-03-16 | Safeguards development and delivery of Securty Design Document on time. | Done
| A21 | Host meeting with testing lead to decide whether or not having employees specialize within a certain branch of testing would aid efficency. | Project Manager | Arib Dhuka | 2021-05-05 | 2021-07-27 | 2021-07-02 | This would lead to another action of moving around resources and estimate changes to project schedule and budget | Done

## Decisions
Project Decision List
# | Description | Decision Owner | Decision Date | When Decided, Who was Present
D-1 | Agreed that project would fund Security Training (up to 10k) | Must be a stakeholder | 2020-07-09 | Technical review meeting with Dev Lead, Arch, VP of Delivery, VP of PM, Finance Lead, Sales Lead
D-2 | Approve the design document to begin development | Project Manager | 2021-03-03 | Project Manager, Development Lead, Design Lead, Requirements Lead, Deployment Lead
D-3 | Approve the server system documention place to scale for encompasing current data and future volumes of data for scale. | Project Manager | 2021-12-12 | Project Manager, Development Lead, Design Lead, Requirements Lead, Deployment Lead, OIT DIRECTOR, John Doe, Test Engineers
D-4 | Approve the use of API | Development Lead | 2020-07-09 | Development Lead and Development Team, Project Manager
D-5 | Approve application for testing | Development Lead | 2021-03-05 | Project Manager, Development Team, Development Lead
D-6 | Approve final product quality to finalize release | Deployment Lead | 2021-12-01 | Decision was made during the quality report meeting with Jessica Samuel, James Joseph, Development team, Testing team, Deployment team
D-7 | Approve with stakeholders that the Connect Page is a low priority feature and need not be implemented to shorten the scope/functionality of the project. | Project Manager | 2020-10-30 | Project Manager, Development Lead, Senior Management, FEMA Point of Contact
D-8 | RR - Reject moving the deadline of the project from an extended date due to critical path becoming longer in duration and instead we have moved resources around to accomodate the critical path to be on time for delivery of promised product. | Project Manager | 19- Sept-21 | Project Manager, Development Lead, Senior Management, FEMA Point of Contact
D-9 | MW - Include Testers in security training fund for learning modules on security testing. | Project Manager | 2020-07-11 | Project Manager, Testing Lead, Architect Lead, Testers
D-10 | AD - Decided against making the data acquisition synchronous with the data schema design due to confliction of resources extending the schedule. | Project Manager | 2021-03-25 | Project Manager, Dev_3, Requirements Lead
D-11 | NP - Remove the Connect page UI to ensure the solution is delivered on time, function, and cost. | Project Manager |  | Project Manager, Dev Lead, Test Lead
D-12 | RA - Allow new shelters to create profile pages independently | Development Lead | 2021-06-18 | Project Manager, Developement Lead, FEMA point of contact